## schedule
FMP Schedule
Month | Day | Date | Activity | Production Stage
February | Tuesday | 20 | Brief set | Pre-Prod
| Wedsday | 21
| Thursday | 22 | Literary festival
| Friday | 23
| Monday | 26
| Tuesday | 27
| Wedsday | 28
March | Thursday | 1
| Friday | 2
| Monday | 5
| Tuesday | 6
| Wedsday | 7 | Cam test -12:15
| Thursday | 8
| Friday | 9
| Monday | 12
| Tuesday | 13 | First production meeting - 12:15 - fishbowl
| Wedsday | 14
| Thursday | 15
| Friday | 16
| Monday | 19
| Tuesday | 20
| Wedsday | 21
| Thursday | 22 | Poster Photoshoot
| Friday | 23 | Start pitch by this date // end of spring term
| Monday | 26 | Term holiday
| Tuesday | 27
| Wedsday | 28
| Thursday | 29
| Friday | 30
April | Monday | 2
| Tuesday | 3
| Wedsday | 4
| Thursday | 5
| Friday | 6
| Monday | 9 | Start of summer term
| Tuesday | 10
| Wedsday | 11
| Thursday | 12
| Friday | 13 | FMP Pitch
| Monday | 16
| Tuesday | 17
| Wedsday | 18
| Thursday | 19
| Friday | 20
| Monday | 23
| Tuesday | 24
| Wedsday | 25
| Thursday | 26
| Friday | 27
| Monday | 30 | Filming days | Production
May | Tuesday | 1
| Wedsday | 2
| Thursday | 3
| Friday | 4
| Saturday | 5 | Pickup filming
| Monday | 7 |  | Post
| Tuesday | 8 | Editing
| Wedsday | 9
| Thursday | 10
| Friday | 11 | Voiceover recording
| Monday | 14 | Editing
| Tuesday | 15
| Wedsday | 16
| Thursday | 17
| Friday | 18
| Monday | 21
| Tuesday | 22 | Focus group of 1st cut- 1:15
| Wedsday | 23 | Final edits
| Thursday | 24
| Friday | 25 | Deadline - film & folder